## MOM
Date | Duration | Participant | Description |  |  | Target Date | Remark | Status
2023-01-04 | 25 min | Br.Zaheer | Consolidate the Master Sheet |  |  | 7th Jan 2023
|  | Br.Naiyar | Follow-up Pending Exams
NS Class converted into Advance
2023-02-22 | 40 min | Br.Zaheer | Mahe Ramazan Project | Quran Dua Memorization Book Reading then exam
|  | Br.Naiyar | C Form Followup | Portal Access: http://census.oic.almsoftware.in/authenticate/login?ReturnUrl=%2fclasses z1_secondary ¦ 321
|  |  | Book | Al Mohajja Fi Ma nazala fi Qaem-e-Hujja The Qaem in the Quran Page-upto 52 Ashaab Name - from page 27
Attendence / Quran / Library Followup with Nazim
Exam Tracking
DS3 - Old Paper correction
Date | Duration | Participant | Description |  |  | Target Date | Remark | Status
2024-07-04 | 30 Min | Br.Ashiq | Duscussion on Existing Status of Planning and Achivement 2024
|  | Br.Naiyar | Shared the Link for Paper Status Update:
Login - AIM Exams (almsoftware.in)
NOTE: As suggested AIM credential is not working
Need to followup with Nazim for C Form upload
NOTE: From DS3 Nazim : pls remove Br Saif Lokhandwala's name from registry as he is no more attending match since a year and he moved to canada
Date | Duration | Participant | Description |  |  | Target Date | Remark | Status
2024-08-01 | 10:30 to 11:45 | Br.Ashiq Br.Naiyar | CM to be arrange with Maulana Saheb in Aug 2024, Br.Ashiq is working on it |  |  | 2024-08-01 | 2024-08-10 | Completed
|  |  | Nazim Nizam Nama will be shared by Br.Ashiq |  |  | 2024-08-01
|  |  | Nazim Motivation in Nazim Meeting |  |  | 2024-08-01
|  |  | Nazim Meeting need to arrange in Aug 2024 |  |  | 2024-08-01
|  |  | Nazim change - Need to discuss with Class Teacher |  |  | TBD
|  |  | Conduction of class (Student Class Report) to be sent to Teacher |  |  | TBD | 2024-08-08 | Completed
|  |  | Exam anticipated list to send to Ashiq Br. |  |  | 2024-08-01 |  | In Progress
|  |  | paper Correct Detail shared by Br.Ashiq |  |  | 2024-08-01 |  | Completed
|  |  | https://exams.almsoftware.in/login/oic : Credential will verified by Br.Ashiq |  |  | 2024-08-01 |  | Pending
|  |  | Database of Email Addresses of all Sec Brs to be maintained - Br.Naiyar is working |  |  | 2024-08-01 |  | In Progress
|  |  | Specific books relating to current Aqaed in classes to be provided to Brs. - Discuss with Nazim - Br.Naiyar |  |  | 2024-08-01 |  | Pending
|  |  | Clas IH-1 (Mumbai) - Need class detail of Br.Rahbar ¦ Inform to Br.Ashiq on 5th Aug 2024 |  |  |  |  | Pending
Date | Duration | Participant | Description |  | Responsible | Target Date | Remark | Status
2024-09-03 | 10:30 to 11:25 PM | Br.Ashiq Br.Naiyar Br.Murtuza Br.Taha | Nazim Nizam Nama will be shared by Br.Ashiq |  | Br.Ashiq | 2024-08-01
|  |  | Nazim Motivation in Nazim Meeting |  |  | 2024-08-01
|  |  | Nazim Meeting need to arrange in Aug 2024 |  |  | 2024-08-01
|  |  | Nazim change - Need to discuss with Class Teacher (AUH-1) |  |  |  |  | Requested
|  |  | https://exams.almsoftware.in/login/oic |  | Br.Ashiq |  |  | Completed
|  |  | Clas IH-1 - Br.Rahbar (Mumbai) - Need class detail of Br.Rahbar ¦ Inform to Br.Ashiq on 5th Aug 2024 |  | Br.Ashiq |  |  | Waiting
|  |  | Inspection for Class (DS5) |  | Br. Ashiq |  |  | Completed
|  |  | Eid-E-Zehra (Internal Program) - Motivation to Brs. Article share to Class and Quiz need to be conduct in IP |  | Team Work
Date | Duration | Participant | Description |  | Responsible | Target Date | Status | Remark
2024-09-09 | 10:30 to 11:25 PM | Br.Ashiq Br.Naiyar Br.Murtuza | Follow Up Brs (DS5)
|  |  | Tanveer Br |  | Br. Murtuza | 2024-09-14
|  |  | Muntazir Br |  | Br. Murtuza | 2024-09-14
|  |  | Hasan Bhai Sorathiya |  | Br.Murtuza | 2024-09-14
|  |  | Hasan Sayyed Br |  | Br.Ashiq | 2024-09-14
|  |  | Hyder Br |  | Br.Ashiq | 2024-09-14
|  |  | Shujaat Br. |  | Br.Ravish | 2024-09-14
|  |  | MCQ Exam Detail need to share to br.Ashiq |  | Br.Naiyar | 2024-09-11
|  |  | Arrange - MCQ Exam Link |  | Br.Ashiq | 2024-09-14
|  |  | New books to be introduced via drop box.(Teacher to be requested) |  | Br.Ashiq
|  |  | Nazim change - Need to discuss with Class Teacher (AUH-1) |  | Br.Ashiq |  | Requested
|  |  | Clas IH-1 - Br.Rahbar (Mumbai) - Need class detail of Br.Rahbar ¦ Inform to Br.Ashiq on 5th Aug 2024 |  | Br.Ashiq |  | Waiting
|  |  | Inspection for Class (DS3) |  | Br.Ashiq | 2024-09-14
|  |  | Eid-E-Zehra (Internal Program) - Prepare MCQ |  | Team Work
|  |  | Best Teacher Peformance |  | Br.Ashiq
Test123 | 1234

## Weekly
# | Description | Responsible | 2024-09-08 | 2024-09-15 | 2024-09-22 | 2024-09-29 | 2024-10-06 | 2024-10-13 | 2024-10-20 | 2024-10-27
Conduction data every Week - Short Message in Grp (Class Yes / No)
| AUH - Friday 8 PM | Br.Murtuza | 2024-09-08: Yes
| DS3 - Friday 6 PM | Br.Murtuza | 2024-09-08: Yes
| DS5 - Sunday 9 AM | Br.Murtuza | 2024-09-08: Yes

## Monthly
# | Description | Responsible | 2024-09-30 | 2024-10-30 | 2024-11-30 | 2024-12-30
1 | Exam anticipated list to send to Ashiq Br. | Br.Naiyar
2 | Database of Email Addresses of all Sec Brs to be maintained | Br.Naiyar
3 | Specific books relating to current Aqaed in classes to be provided to Brs. - Discuss with Nazim | Br.Naiyar
4 | C Form Entry Status in Software | Br.Naiyar
5 | Planning and Achievement | Br.Naiyar
6 | Intreme Report - Share with Br.Ashiq | Br.Naiyar
7 | Status of Pending Exam Report - Share with Br.Ashiq | Br.Naiyar
8 | Status of Pending Exam Followup | Br.Taha
9 | Class of the Month - share to Br.Ashiq | Br.Naiyar
10 | List of Ir-regular Student - Monthly Report share in Group | Br.Naiyar
11
Follow Up Brs (DS5)
| Tanveer Br | Br. Murtuza
| Muntazir Br | Br. Murtuza

## Exam Link
# | Class | Exam Name | Exam Link
| AUH1 | Tauheed - CH1 | https://docs.google.com/forms/d/e/1FAIpQLSeiR7CnUhYgs1aQZ5jZ8w2lvNjrtKbNCdOJv1KYWMmagUdOTA/viewform?usp=sharing
| AUH1 | Tauheed - CH2 | https://docs.google.com/forms/d/e/1FAIpQLSfZuj4T830QW3YkQn1xh7iBMrFZG64s_-Z2Kv3EvMKah4iCmw/viewform?usp=sharing
| AUH1 | Tauheed - CH3
| AUH1 | Nahv-1
| AUH1 | TI-3A